## Goal Strategy Action List
ID | Level | GoalStrategyAction | Responsible Committee | Supporting Committee | Mandate (summary) | Detailed Mandate | Current State (existing /limited /new) | Feasible with current resources? (yes/maybe/ no) | Priority | Timing (Immediate/ Future) | Comments | Suggested Deliverable/Metrics/Outcome | Start Date | End Date | % Complete | Status
1.0.0 | Goal | Advise. Serve as a trusted advisor to policymakers, media, and the public to develop and evaluate statewide programs and policies. | Research and Analysis | Policy and Planning | [6 empty] | In the past committee has not been very active.
1.1.0 | Strategy | Develop a research agenda | Research and Analysis | Executive | Identify causes and effects, and increase awareness | Work to identify causes and effects of homelessness and increase awareness among policymakers and the general public | New | Yes | Quick Win | Immediate | Input from other committees | Research agenda is produced by end of Y1 Knowledge base of issues related to homelessness is created and shared widely by end of Y5
1.1.1 | Action | Identify and network with researchers across the state of Iowa to identify overlaps in ICH priorities and funded research (including ICA)
1.1.2 | Action | Create a process for vetting, evaluating, and prioritizing research
1.1.3 | Action | Perform a needs assessment of existing and needed research | [8 empty] | Evaluate and determine if the Community Solutions “Built for Zero” data-driven approach to homelessness should be implemented (BoS decided to pass in 2021 when approached by Community Solutions).
1.1.4 | Action | Build a knowledge base of issues related to homelessness beyond services/CoC
1.2.0 | Strategy | Coordinate research | Research and Analysis | Executive | Biennial report to the Governor and Gen. Assembly | The council shall prepare and file with the governor and the general assembly on or before the first day of December in each odd-numbered year, a report on homelessness in Iowa | Limited | Maybe | Transformational | Future | ICA is limited in ability to provide support around this strategy. Need for more resources | Research is produced
1.2.1 | Action | The council shall prepare and file with the governor and the general assembly on or before the first day of December in each odd-numbered year, a report on homelessness in Iowa | [8 empty] | Need to consider cost implications on various systems of homelessness. Possible topics: (Cost of Homelessness, lack of affordable housing, loss of housing)
1.2.2 | Action | Clarify the role of the ICH in assisting with the completion of the state's continuum of care applications to the United States Department of Housing and Urban Development | Executive | [7 empty] | Consider changing statute (applications)
1.2.3 | Action | Clarify relationship between the ICH and the Institute for Community Alliances
1.2.4 | Action | Consider providing grants to fund evaluations of innovative approaches
1.2.5 | Action | Develop systems for coordinating cross-system data sharing
1.2.5 | Action | Review SPPG Document
1.3.0 | Strategy | Create a clearinghouse/library for objective information related to homelessness | Research and Analysis | Public Awareness | Identify causes and effects, and increase awareness | Work to identify causes and effects of homelessness and increase awareness among policymakers and the general public | New | No | Thankless Task | Future (maybe) |  | Library is produced
1.3.1 | Action | Determine the cost of developing a resource to house objective research on homelessness
1.3.2 | Action | Compile information on evidence-based practices
1.4.0 | Strategy | Develop and publish an annual Statewide Action Plan | Policy and Planning | Research and Analysis | Annual recommendations | The council shall make annual recommendations to the governor regarding matters which impact homelessness on or before September 15 | New | No | Transformational | Future | Need to look at how Statewide Action Plan is resourced. Work is contingent on other plan elements. | Statewide Action Plan is produced
1.4.1 | Action | Convene interagency ICH members to develop a statewide action plan
1.4.2 | Action | Use statewide action plan to drive policy advocacy efforts
1.5.0 | Strategy | Meet with policymakers to share information and offer evidence-based solutions | Policy and Planning | Research and Analysis | Advise Governor, IFA, State agencies, and private orgs | Advise the Governor's Office, IFA, state agencies, and private organizations on strategies to prevent and eliminate homelessness | Limited | Yes | Transformational | Immediate | Public Awareness may also be involved and support here. State departments can give input, but state department staff cannot meet with legislators. | # of meetings # of policies changed # of resources disseminated
1.5.1 | Action | Identify ICH champions at the state and local government levels and establish relationships
1.5.2 | Action | Develop a process for monitoring and disseminating information about legislation and other policy developments at the state and local levels
1.5.3 | Action | Provide clear, objective information about evidence-based solutions to ending homelessness
1.5.4 | Action | Set up meetings with champions to provide information and build trust
2.0.0 | Goal | Educate. Change public perception of the experience of homelessness to create increased compassion and shared ownership over solutions to end homelessness. | Public Awareness | Research and Analysis
2.1.0 | Strategy | Develop and launch broad public awareness campaigns | Public Awareness | Research and Analysis | Identify causes and effects, and increase awareness | Work to identify causes and effects of homelessness and increase awareness among policymakers and the general public | Limited | Yes | Transformational | Immediate |  | # of campaigns developed and launched # of resources created Amount of funding secured
2.1.1 | Action | Find funding to support public awareness activities
2.1.2 | Action | Create a marketing and communications plan for ICH public awareness campaigns
2.1.3 | Action | Create and disseminate information to raise awareness and build empathy among the public about the true lived experience of homelessness
2.1.4 | Action | Disseminate information/publications about chronic homelessness in Iowa
2.1.5 | Action | Reduce stigma and dispel myths and misconceptions through public awareness campaigns
2.1.6 | Action | Coordinate public awareness campaigns with partner campaigns (i.e. mental health awareness month)
2.1.7 | Action | Create education and awareness resources for local CoCs to use to educate community partners
2.2.0 | Strategy | Develop and launch targeted campaigns | Public Awareness | Research and Analysis | Identify causes and effects, and increase awareness | Work to identify causes and effects of homelessness and increase awareness among policymakers and the general public | New | No | Transformational | Future | Need to scope out the targeted campaigns before determining feasibility with current resources. | # of campaigns developed and launched # of resources created
2.2.1 | Action | Raise awareness about the reality/”faces” of rural homelessness in Iowa (e.g., DV/at risk of eviction, doubling up, tenting in backyards)
2.2.2 | Action | Educate stakeholders about the cyclical relationship between substance use disorder, mental health, corrections, and homelessness
2.2.3 | Action | Educate stakeholders about the impact on communities and individuals of the criminalization of homelessness
2.2.4 | Action | Educate landlords about available eviction prevention resources
2.2.5 | Action | Educate landlords about renting to households with subsidies
2.2.6 | Action | Elevating awareness of correlation between housing cost and wages (2021 Out of Reach Report)
2.2.7 | Action | Highlight costs of racial disparities in homelessness in Iowa through public awareness campaigns
2.3.0 | Strategy | Highlight and publicize proven programs and policies | Public Awareness | Research and Analysis | Identify and prioritize efforts | Use existing resources to identify and prioritize efforts to prevent persons from becoming homeless and to eliminate factors that keep people homeless. | New | Yes | Quick Win | Immediate |  | # of case studies produced and published # of white papers produced and published
2.3.1 | Action | Communicate impact of successful programs/models and advocate for additional resources: National Housing Trust Fund (NHTF) Permanent Supportive Housing Rapid Rehousing Homeless Veteran Reintegration Grant Program (DOL Grant) Healthy Homes HUD Youth Homelessness Demonstration Program Housing First
2.3.2 | Action | National Housing Trust Fund (NHTF)
2.4.0 | Strategy | Provide materials and information to homeless service providers to establish a baseline for service provision | Public Awareness | Policy and Planning | Develop service delivery system | Work to develop a coordinated and seamless service delivery system to prevent and alleviate homelessness | Limited | Maybe | Fill-in | Future | Advise funding organizations (foundations and government) on how to use these materials | # of resources produced and shared
2.4.1 | Action | Review SPPG Document : Revise and reissue standards of practice for homeless services, addressing challenges specific to impacted sub-populations (older adults, LGBTQ+ youth and adults, BIPOC, persons without documentation, etc.).
2.4.2 | Action | Provide information and resources to faith-based organizations and other community stakeholders on service standards of practice and information about funding
3.0.0 | Goal | Connect. Work to eliminate service gaps by building access, trust, and transparency across systems | Policy and Planning | Research and Analysis | [6 empty] | This goal may require a new committee or revisions to the committee scope of work. Strong involvement needed from state agency reps. | 0
3.1.0 | Strategy | Map state-level resources (funding and programs) to identify cross-system gaps, silos, and barriers by engaging in system mapping | Research and Analysis |  | Identify and use funding | Identify and use federal and other funding opportunities to address and reduce homelessness within the state | New | Maybe | Transformational | Future |  | Document is produced by end of Y2 identifying all funding, resources, and programs available through state agencies, identifying overlapping services, service gaps, and opportunities to improve
3.1.1 | Action | Map stakeholders and available resources across healthcare, SUD, mental health, education, corrections, reentry, workforce development, veterans, housing, and homelessness services systems
3.1.2 | Action | Develop a partnership with 211 to support system mapping and ensure critical resources are in their system
3.1.3 | Action | Seek out and obtain funding to connect and integrate systems
3.1.4 | Action | Identify challenges with network coordination (entry to and discharge from homeless services and other systems, including long term care, assisted living, etc.)
3.1.5 | Action | Coordinate with other system mapping efforts (i.e., CoC board)
3.2.0 | Strategy | Identify and focus annually on one or two systems to improve coordination (healthcare, behavioral health, education, corrections/reentry, workforce development, housing, etc.) | Policy and Planning |  | Evaluate efficient coordination of state agency resources | Evaluate whether state agency resources could be more efficiently coordinated with other state agencies to prevent and alleviate homelessness | New | Maybe | Transformational | Future
3.2.1 | Action | Identify systems
3.2.2 | Action | Prioritize systems
3.2.3 | Action | Reduce and remove barriers to access by improving coordination across systems
3.3.0 | Strategy | Improve stakeholder outreach and engagement with the ICH | Policy and Planning |  | Evaluate efficient coordination of state agency resources | Evaluate whether state agency resources could be more efficiently coordinated with other state agencies to prevent and alleviate homelessness | Limited | Yes | Quick Win | Immediate |  | # of state agency members who attend 80%+ ICH meetings # of state agency ICH members engaged with committees # of state agency ICH members who participate in ICH meetings
3.3.1 | Action | Ensure state agency members participate actively in ICH meetings
3.3.2 | Action | Support increased collaboration between CoCs and other cross-sector partners at the local level | [8 empty] | Potential for support in identifying funding and encouraging/providing support. Serving as a "connector." Ex. Racial equity work across CoCs (Polk County and ICH)
3.3.3 | Action | Convene statewide, cross-sector public, private, and nonprofit stakeholders beyond ICH membership (in person or virtually) | [8 empty] | Potential overlap with the Housing Iowa Conference
3.4.0 | Strategy | Collect and report on interagency data | Policy and Planning | Research and Analysis | Identify causes and effects, and increase awareness | Work to identify causes and effects of homelessness and increase awareness among policymakers and the general public | New | Maybe | Transformational | Future |  | # of data sharing agreements
3.4.1 | Action | Identify/map out data collected by interagency and cross-sector partners
3.4.2 | Action | Identify goals, restrictions, and processes for sharing interagency data
4.0.0 | Goal | Advocate. Advocate for evidence-based approaches and sufficient levels of funding to ensure housing stability | Policy and Planning | Public Awareness
4.1.0 | Strategy | Build a relationship with intergovernmental affairs staff (legislative laison) within state agencies | Policy and Planning | Executive | Identify and prioritize efforts | Use existing resources to identify and prioritize efforts to prevent persons from becoming homeless and to eliminate factors that keep people homeless. | New | Yes | Transformational | Future | (e.g., Workforce Dev: Deputy Director) Need for more engagement with state agencies.
4.1.1 | Action | Develop and implement process for coordinating with intergovernmental affairs staff within state agencies | [8 empty] | Establish rapport outside of session
4.1.2 | Action | Create a forum for state agency members to discuss RFIs and legislative initiatives | [8 empty] | Could be a legislative bullet point on the meeting agenda
4.1.3 | Action | Evaluate, and as appropriate implement, hiring IGA staff person for ICH
4.2.0 | Strategy | Evaluate existing state policies, programs, statutes, and rules to determine necessary revisions | Policy and Planning | Research and Analysis | Develop process for evaluating state policies/programs | Develop a process for evaluating state policies, programs, statutes, and rules to determine whether any state policies, programs, statutes, or rules should be revised to help prevent and alleviate homelessness | New | No | Transformational | Future | May be owned by new state agency led committee | Document outlining ICH policy agenda produced and approved by ICH by end of Y1. % of position statements completed
4.2.1 | Action | Develop an evaluation process to identify issues with state policies, programs, statutes, and rules
4.2.2 | Action | Implement an annual review process for state policies, programs, statutes, and rules
4.3.0 | Strategy | Develop a proactive policy agenda to inform legislative and executive initiatives (see also 1.5.0) | Policy and Planning | Public Awareness | Develop process for evaluating state policies/programs | Develop a process for evaluating state policies, programs, statutes, and rules to determine whether any state policies, programs, statutes, or rules should be revised to help prevent and alleviate homelessness | New | Maybe | Transformational | Immediate |  | Document outlining ICH policy agenda produced and approved by ICH by end of Y1. % of position statements completed
4.3.1 | Action | Examine and define ICH positions on topics and align positions with annual system focus
4.3.2 | Action | Identify and advise on anticipated legislative and executive initiatives
4.3.3 | Action | Prepare materials to support advocacy related to legislative initiatives (fact sheets, position statements, white papers, etc.)
5.0.0 | Goal | Sustain. Create an effective, sustainable, accountable governance structure for the ICH. | Executive | Nominating
5.1.0 | Strategy | Build governance capacity within the ICH | Executive |  |  | #N/A | Existing | Yes | Transformational | Immediate |  | Revised Governance Charter recommended Revised policies and procedures created and accepted
5.1.1 | Action | Revise the ICH governance charter | [8 empty] | Governance charter is created by the ICH and can be changed. Changes to Administrative Rule and statute need to go through higher levels of approval, starting with IFA.
5.1.2 | Action | Seek out opportunities for board development
5.1.3 | Action | Manage the processes of nominating and evaluating the board chair
5.1.4 | Action | Manage conflicts of interest and ethics issues that arise on the ICH
5.1.5 | Action | Consider the use of a board portal to store important documents and materials
5.1.6 | Action | Identify job descriptions/roles and responsibilities for members
5.1.7 | Action | Create policies (i.e., for who has authority to speak on behalf of the ICH)
5.2.0 | Strategy | Build internal capacity (staffing and funding) | Executive |  |  | #N/A | New | Maybe | Transformational | Immediate | Committees are responsible, but with IFA support | Request for additional staffing support and funding is submitted to IFA Annual budget request process is developed Budget request is submitted annually
5.2.1 | Action | Examine and obtain the level of administrative support needed to sustain the ICH activities
5.2.2 | Action | Identify American Rescue Plan (ARP) funds that can support ICH sustainability
5.2.3 | Action | Estimate the amount of dedicated staff time needed to implement the strategic plan | [8 empty] | Additional budget does not include the staffing resources.
5.2.4 | Action | Advocate for dedicated staff resources to support administration of the ICH (Functions: Executive Director, Intergovernmental Affairs, Policy Analyst, Data Analyst, Communications, Admin) | [8 empty] | May be some precedent with Child Advocacy Board.
5.2.5 | Action | Develop an annual budget request process based on the cost of yearly priorities | [8 empty] | Current budget of ~$50k is through IFA; discrete initiatives are funded.
5.3.0 | Strategy | Examine and revise committee structure | Executive |  |  | #N/A | Limited | Yes | Quick Win | Immediate | Committees that are in statute would need change to statute | New organizational chart is created
5.3.1 | Action | Consider aligning committee structure with strategic plan goals (advise, educate, connect, advocate, sustain)
5.3.2 | Action | Identify an organization chart
5.4.0 | Strategy | Create a flexible and adaptable structure for the ICH moving forward | Executive | Nominating |  | #N/A | New | Yes | Transformational | Immediate | Strategy must be conducted in consultation with IFA staff and state agency members | A decision is made by end of Y1 regarding location of ICH A process is instituted for conducting an annual review of the Iowa Code and Administrative Rule and recommending changes. Recommended changes are submitted to IFA by end of Y1
5.4.1 | Action | Examine, evaluate, and make recommendations regarding the location of the ICH under state government in a manner that ensures stability, nonpartisanship, and objectivity.
5.4.2 | Action | Create a process for regularly reviewing and recommending revisions to the Iowa Code and Administrative Rule
5.4.3 | Action | Evaluate membership requirements of the ICH in the Iowa Code and make recommendations for changes (size, state participation, CoC role/representation) | Nominating | [7 empty] | Support this by strengthening relationship with Governor's Office
5.5.0 | Strategy | Develop and implement a plan for incorporating, supporting, and developing meaningful engagement with people with diverse, lived experiences representative of homelessness on the Council | Nominating | Executive |  | #N/A | Existing | Maybe | Quick Win | Immediate | Support this by strengthening relationship with Governor's Office. Need for avoiding tokenism and building meaningful systems to support engagement. | Recruiting and onboarding strategy is developed. Recruiting and onboarding strategy is implemented Feasibility of securing funding is determined.
5.5.1 | Action | Develop and implement a comprehensive recruiting and onboarding strategy for persons with lived experience of homelessness
5.5.2 | Action | Consider adopting a “Lived Experience Advisory Board” (LEAB) model to advise the ICH | [8 empty] | Background check process is a barrier to bringing on members with lived experience - LEAB may be a way of working around this.
5.5.3 | Action | Determine feasibility of securing funding to compensate individuals with lived experience for board service/membership (in consultation with Gov's office) | [8 empty] | Funding not currently available
5.5.4 | Action | Implement the plan
5.6.0 | Strategy | Develop technology to support activities | Executive | Public Awareness |  | #N/A | Limited | Maybe | Transformational | Future | With advice from ICA. Close collaboration with IFA. | Secure funding and set up portal for members by end of Y2 Memo with recommended website changes is submitted to IFA by end of Y1
5.6.1 | Action | Evaluate process to create an internal system or portal for ICH members to use to communicate and coordinate information and make recommendations to IFA |  | Research and Analysis | [6 empty] | Past challenge has been maintaining internal systems. IFA has pushed back on in the past and would in the future without a clear plan for implementation
5.6.2 | Action | Revise the public-facing ICH website to align with the strategic plan goals (host research, case studies of evidence-based practices, directory of resources, meeting agendas, etc.) |  | Public Awareness | [6 empty] | Will need dedicated staff time to maintain. Need to ensure the website is developed and maintained.

## Analysis
# of Goals Per Committee |  |  | # of Strategies Per Committee
Count of GoalStrategyAction | Column Labels |  | Count of GoalStrategyAction | Column Labels
Row Labels | Goal | Grand Total | Row Labels | Strategy | Grand Total
Executive | 1 | 1 | Executive | 5 | 5
Policy and Planning | 2 | 2 | Nominating | 1 | 1
Public Awareness | 1 | 1 | Policy and Planning | 8 | 8
Research and Analysis | 1 | 1 | Public Awareness | 4 | 4
Grand Total | 5 | 5 | Research and Analysis | 4 | 4
|  |  | Grand Total | 22 | 22
Feasible with current resources?
Row Labels | Count of GoalStrategyAction
Strategy | 22
Maybe | 9
No | 4
Yes | 9
Grand Total | 22
Feasible with current resources?
Row Labels | Count of GoalStrategyAction
Strategy | 22
Future | 10
Immediate | 11
Future (maybe) | 1
Grand Total | 22
Level | Strategy
Row Labels | Count of GoalStrategyAction
Immediate | 11
Executive | 4
Build governance capacity within the ICH | 1
Build internal capacity (staffing and funding) | 1
Create a flexible and adaptable structure for the ICH moving forward | 1
Examine and revise committee structure | 1
Nominating | 1
Develop and implement a plan for incorporating, supporting, and developing meaningful engagement with people with diverse, lived experiences representative of homelessness on the Council | 1
Policy and Planning | 3
Develop a proactive policy agenda to inform legislative and executive initiatives (see also 1.5.0) | 1
Improve stakeholder outreach and engagement with the ICH | 1
Meet with policymakers to share information and offer evidence-based solutions | 1
Public Awareness | 2
Develop and launch broad public awareness campaigns | 1
Highlight and publicize proven programs and policies | 1
Research and Analysis | 1
Develop a research agenda | 1
Future | 10
Executive | 1
Develop technology to support activities | 1
Policy and Planning | 5
Build a relationship with intergovernmental affairs staff (legislative laison) within state agencies | 1
Collect and report on interagency data | 1
Develop and publish an annual Statewide Action Plan | 1
Evaluate existing state policies, programs, statutes, and rules to determine necessary revisions | 1
Identify and focus annually on one or two systems to improve coordination (healthcare, behavioral health, education, corrections/reentry, workforce development, housing, etc.) | 1
Public Awareness | 2
Develop and launch targeted campaigns | 1
Provide materials and information to homeless service providers to establish a baseline for service provision | 1
Research and Analysis | 2
Coordinate research | 1
Map state-level resources (funding and programs) to identify cross-system gaps, silos, and barriers by engaging in system mapping | 1
Future (maybe) | 1
Research and Analysis | 1
Create a clearinghouse/library for objective information related to homelessness | 1
Grand Total | 22

## Policy Agenda List
Preliminary Policy Agenda
ID | Level | GoalStrategyAction
1 | Strategy | Advocate for adopting a Housing First approach
1.1 | Action | Develop and share outreach materials highlighting objective data on the housing first approach
1.2 | Action | Ensure advocacy efforts align with and support a housing first approach
2 | Strategy | Advocate for increasing the supply of deeply affordable, safe, quality housing
2.1 | Action | Advocate for more resources for permanent supportive housing
2.2 | Action | Advocate for more resources for rapid rehousing
2.3 | Action | Target advocacy to increasing the supply of housing affordable to households at below 30% AMI and on fixed incomes
2.4 | Action | Advocate for increasing the dedicated subsidies at the state level for deeply affordable housing (0-30% AMI)
2.5 | Action | Advocate for increasing the supply of deeply affordable housing in rural communities
2.6 | Action | Advocate for creating and preserving safe, healthy housing resources for aging in place
2.7 | Action | Advocate for more housing subsidies/vouchers
2.8 | Action | Advocate for bringing additional federal senior housing subsidies/resources to Iowa
3 | Strategy | Advocate for preservation of subsidized and non-subsidized affordable hoursing
3.1 | Action | Advocate for preserving the supply of subsidized deeply affordable, safe, quality housing (0-30% AMI)
3.2 | Action | Advocate for preservation of smaller, naturally affordable units (ADUs, manufactured housing, granny flats, etc.)
3.3 | Action | Collect and disseminate information on best practices for creating and preserving affordable housing
4 | Strategy | Advocate for increasing access to affordable housing and eviction prevention
4.1 | Action | Promote fair housing practices
4.2 | Action | Secure dedicated funding for landlord outreach and education about available services, especially in rural communities
4.3 | Action | Advocate for continued flexibility in funding for affordable housing and vouchers
4.4 | Action | Advocate for continued, flexible funding for eviction prevention
4.5 | Action | Support increasing resources (funding/staffing) for homelessness prevention services (legal, landlord dispute resolution/mediation)
5 | Strategy | Advocate for increased funding and access to quality support services
5.1 | Action | Develop and widely share a resource identifying the amount of funding needed for critical services (i.e., reentry services, flexible funding for wraparound services, employment services, fully funded school liaison program, etc.)
5.2 | Action | Advocate for increased access to services (service accessibility, transportation, addressing barriers to care)
5.3 | Action | Provide guidance and resources to service providers to support evaluation of programs against standards of care that emphasize evidence-based, trauma-informed practices; a harm reduction approach; and an equity lens in program evaluation

## Data Validation Lists (hidden)
Committee Names | Current State | Status | Mandate Summary | Detailed Mandate
Executive | Existing | Complete | Develop service delivery system | Work to develop a coordinated and seamless service delivery system to prevent and alleviate homelessness
Nominating | Limited | In progress | Identify and use funding | Identify and use federal and other funding opportunities to address and reduce homelessness within the state
Research and Analysis | New | Not started | Identify and prioritize efforts | Use existing resources to identify and prioritize efforts to prevent persons from becoming homeless and to eliminate factors that keep people homeless.
Policy and Planning |  | Behind schedule | Identify causes and effects, and increase awareness | Work to identify causes and effects of homelessness and increase awareness among policymakers and the general public
Public Awareness |  | Postponed | Advise Governor, IFA, State agencies, and private orgs | Advise the Governor's Office, IFA, state agencies, and private organizations on strategies to prevent and eliminate homelessness
Continuum of Care |  |  | Evaluate efficient coordination of state agency resources | Evaluate whether state agency resources could be more efficiently coordinated with other state agencies to prevent and alleviate homelessness
|  |  | Develop process for evaluating state policies/programs | Develop a process for evaluating state policies, programs, statutes, and rules to determine whether any state policies, programs, statutes, or rules should be revised to help prevent and alleviate homelessness
|  |  | Annual recommendations | The council shall make annual recommendations to the governor regarding matters which impact homelessness on or before September 15
|  |  | Biennial report to the Governor and Gen. Assembly | The council shall prepare and file with the governor and the general assembly on or before the first day of December in each odd-numbered year, a report on homelessness in Iowa
|  |  | CoC application | The council shall assist in the completion of the state's continuum of care application to the United States Department of Housing and Urban Development
|  |  | Executive committee | Executive Committee (31.1(5) see statute).
|  |  | Nominating committee | Nominating Committee (31.1(5) see statute).
31.1(5) Committees. The council shall form an executive committee consisting of the council’s chairperson, vice chairperson, and seven members, one of whom shall be the immediate past chairperson if a current member of the council. The chairperson shall appoint the remaining members of the executive committee. The executive committee shall be responsible for reviewing and making recommendations for amendments or changes to the internal rules of procedure. The executive committee shall carry out the business of the council between regularly scheduled council meetings. A majority of the members of the executive committee shall constitute a quorum. Any action taken by the executive committee must be adopted by an affirmative vote of a majority of its members.
Nominating committee. The nominating committee shall initially consist of all 12 agency director members. Following the initial appointment of the general public members to the council, the council shall annually at its March meeting elect six members, three of whom shall be agency director members and three of whom shall be general public members. The chairperson of the council shall also be a voting member. The nominating committee shall nominate persons to the governor to fill the general public member positions when they become open. A majority of the members of the nominating committee shall constitute a quorum. Any action taken by the nominating committee must be adopted by an affirmative vote of a majority of its members.